## Sheet1
AlfaCOR | Primary application is a phython script which deploys a GUI on the AlfaCOR unit LED Screen and read sensor data and writes to mongo database |  | Status
1 | Some Sensor readings do not show reliably for examble the altitude shows 400000+m |  | Pending
2 | Some sensor do not give any readings and there is no way to troubleshoot |  | Pending
3 | Firmware appication conumes more CPU overtime generating heat in the box. This needs to be checked |  | Pending
4 | The GUI has to be improved of the AlfaCOR for the small Screen |  | Pending
5 | Control button don’t work when the AlfaOPS loads - Overaride option |  | Pending
6 | Mongo DB backup and purges |  | Pending
AlfaOPS | Primary Operator Software which collects data via C++ Backend from AlfaCOR Database and displays on GUI using React Frontend
1 | Left Panel to have Menu For AlfaOPS Aerostst Systems Selection Alfa6 Aerostat Systems 1-AlfaFLX 1500 Aerostat System 2-AlfaFLX 2200 Aerostat System 3-AlfaSPR 400 Aerostat System 4-AlfaSPR 600 Aerostat System Other Aerostat Systems 2-Legacy 15M Aerostat System (ADASI) 3-Legacy 17M Aerostat System (TCOM) 4-Legacy 32M Aerostat System (TCOM) | Left Panel | Pending
2 | Left Panel to have Menu for Maintenance 1-Inspections 2-Helium Management 3-Parts Management 4-Maintenance Tools | Left Panel | Pending
3 | Left Panel to have Analysis & Reporting Menu | Left Panel | Patially Completed
4 | Units should be able to be chosen and changed for example Meters to Feet, m/s to knots C to F Kg to lbs | Main Dashboard | Completed/Feedback | Rather than drop down maybe click to change
5 | Aerostst Position and Orientation Widget - Pitch should be up and Roll should be down Maps until GPS readings are not received should show default in Abu Dhabi | Main Dashboard | Completed
6 | Weather Station and Wind Speed Widgets These widgets have to be revamped into two 1-Wind Data Which represents the the Wind Speed Guage and a compass showing Heading and Wind Angle 2-Weather Data Which Shows three Guages Outside Air Temperature, Outside Air Humidity and Out Side Air Pressure | Main Dashboard | Pending
7 | Alfa6 LTA Logo Has to be Changed | Main Dashboard | Completed/Feedback | Left menu still has old logo
8 | Important Point is that the Main Page will be a dashboard at 1080P resolution so alignment and size has to consider this and to avoid any scrolling | Main Dashboard | Completed/Feedback | Spacing and alignment moves based on reading decimal points
9 | Other Label Updates Pressures (inWG) to Pressure Readings, Lift Force to Lift - Ballonet Air to Ballonet Pressure - Remove Live date | Main Dashboard | Completed
10 | Right Panel to be Fixed With Blowers Strobe lights and Payload | Right Panel | Completed/Feedback | The icons provided were not used, also need to have labels as icons only not enough
11 | Right Panel to have configuration menu for Primary Blower Auto settings based on Hull/Ballonet Pressure | Right Panel | Pending
12 | Top Status BAR to have Connected Green for Tether and Green for Wireless which is 10.85.5.85 and the ablitity to siwtch if tether not reachable | Top Bar | Pending
AlfaMNT | This Menu Option will open pages for Technicians to do Inspections, record helium, do sparepart changes and notes |  | Pending
1 | Selecting Inspection Menu will provide 4 forms as per the file to input data and save to alfaCOR as a new colelction |  | Pending
2 | Helium Management will have three apps suchs as Inflation, top up, and Deflation the forms will be provided a placeholder can be provisions |  | Pending
3 | This Parts Management will have a predefined list of parts which were installed on the system and will maintain part number serial number installation date check out and check in with nots for maintenance |  | Pending